International School

Project Plan Document

Course: System Integration Practices

Project Title: Integrated HR & Payroll Dashboard System for Company X

Case Study 1: Problem Statements
Version: 1.0
Date: 27/01/2026

Group: Thrainh / 5
Semester: 2 – 2026
Instructor: MSc. Nguyen Dang Quang Huy
Team Members:

| Thong, Le Huu | -29219038101 |
| --- | --- |
| Minh, Vo Van | -29219261748 |
| Doan, Ba Rin | -29219037721 |
| Tai, Su Phat | -29211162809 |
| Vinh, Nguyen Tran Xuan | - 29211138585 |

Approved by

MSc Huy, Nguyen Dang Quang

Group Project - Instructor:

Name						Signature			Date

Da Nang 02/2026

| Project Acronym | HRD |  |  |  |
| --- | --- | --- | --- | --- |
| Project Title | Company X – Integrated HR & Payroll Management Dashboard |  |  |  |
| Start Date | 25 Jan 2026 | End Date | 1 Feb 2026 |  |
| Lead Institution | International School, Duy Tan University |  |  |  |
| Role | Name | Email |  | Phone |
| Project Mentor | Nguyen Dang Quang Huy |  |  |  |
|  | Le Huu Thong | bass030196@gmail.com |  | 0768463655 |
|  | Su Phat Tai | phattai0935@gmail.com |  | 0766657942 |
|  | Doan Ba Rin | doanbarin@gmail.com |  | 0766721747 |
|  | Nguyen Tran Xuan Vinh | xuanvinh2005nh@gmail.com |  | 0845015537 |
|  | Vo Van Minh | vanminhvo2005@gmail.com |  | 0707944067 |

DOCUMENT NAME

| Document Title | Project Plan Document |  |  |
| --- | --- | --- | --- |
| Reporting Period | February - 2026 |  |  |
| Author(s) | Le Huu Thong Vo Van Minh Su Phat Tai Doan Ba Rin Nguyen Tran Xuan Vinh |  |  |
| Role | Developer |  |  |
| Date | 27/01/2026 | File name | 2. Project Plan Document_IEEE 830-1998.docx |

DOCUMENT APPROVALS

Document Approvals: The following signatures are required for approval of this document.

| Mentor | Huy, Nguyen Dang Quang | Signature: |  |
| --- | --- | --- | --- |
|  |  | Date: |  |
| Team member(s) | Thong, Le Huu | Signature: |  |
|  |  | Date: |  |
|  | Tai, Su Phat | Signature: |  |
|  |  | Date: |  |
|  | Minh, Vo Van | Signature: |  |
|  |  | Date: |  |
|  | Rin, Doan Ba | Signature: |  |
|  |  | Date: |  |
|  | Vinh, Nguyen Tran Xuan | Signature: |  |
|  |  | Date: |  |

TABLE OF CONTENTS

1. Introduction	6

1.1 Purpose of the Document	6

1.2 Scope of the Document	6

1.3 Definitions, Acronyms, Abbreviations	6

1.4 References	6

1.5 Overview	7

2. Project Organization	7

2.1 Team Structure	7

2.2 Stakeholders	8

3. Project Scope and Deliverables	8

3.1 Project Objectives	8

3.2 Project Deliverables	8

3.3 Work Breakdown Structure (WBS)	9

3.4 Development Process	10

3.4.1 Overview	10

3.4.2 Lifecycle Phases	10

3.4.4 Iteration and Review Cycles	11

3.4.5 Tools and Development Environment	12

4. Schedule and Milestones	12

5. Resource and Tools Plan	13

5.1 Software and Tools	13

5.2 Human Resources	13

6. Risk Management	14

7. Quality and Communication Plan	15

7.1 Quality Assurance	15

7.2 Communication Plan	16

8. Change Control Process	16

9. Project Closure	18

10. Appendix	19

## 1. Introduction

### 1.1 Purpose of the Document

The purpose of this document is to establish a comprehensive management framework for the project 'Company X – Integrated HR & Payroll Management Dashboard. The document focuses on describing how to manage the project by defining scope boundaries, developing a detailed implementation schedule, allocating human resources, and establishing risk control measures. The target audience includes the supervising lecturer and the student group.

### 1.2 Scope of the Document

This document focuses on planning, managing, and monitoring the development of the "Integrated HR & Payroll Management Dashboard" system to meet the business needs of Company X. Specifically, the document defines the scope of work to be performed, including integrating data from two separate sources: SQL Server (HUMAN_2025) and MySQL (PAYROLL), and establishing a roadmap for building a RESTful API to ensure automatic data synchronization between the systems. In addition, the management scope also covers monitoring the development progress of the centralized Web Dashboard interface with visual reporting and automatic alert features, along with establishing user authentication and authorization mechanisms to secure data, without going into detailed descriptions of source code or physical infrastructure configuration.

### 1.3 Definitions, Acronyms, Abbreviations

| Term | Definition |
| --- | --- |
| HR | Human Resources |
| API | Application Programming Interface |
| JWT | JSON Web Token |
| REST | Representational State Transfer |
| BRD | Business Requirement Document |
| SRS | Software Requirements Specification |
| CRUD | Create, Read, Update, Delete |

### 1.4 References

- MSc. Nguyen Dang Quang Huy, "Course Lectures: System Integration Practices," International School, Duy Tan University, 2025.

- Company X Management, "Case Study 1: Problem Statements & CEO Memo," Project Documentation, 2024.

- IEEE Computer Society, "IEEE Std 1058-1998: Standard for Software Project Management Plans," 1998.

### 1.5 Overview

Section 1: Introduction

Section 2: Project Organization

Section 3: Project Scope and Deliverables

Section 4: Schedule and Milestones

Section 5: Resource and Tools Plan

Section 6: Risk Management

Section 7: Quality and Communication Plan

Section 8: Change Control Process

Section 9: Project Closure

## 2. Project Organization

### 2.1 Team Structure

| Name | Role | Responsibilities |
| --- | --- | --- |
| Le Huu Thong | PM | Oversees schedule, communication, and task coordination. |
| Doan Ba Rin | Backend | Develops integrated APIs, connects SQL Server and MySQL, handles data synchronization logic and security. |
| Su Phat Tai | Tester | Creates the Test Plan, performs API Unit Testing, and verifies data integrity between the two systems. |
| Nguyen Tran Xuan Vinh | Frontend | Designs the Dashboard UI/UX, displays reporting charts, and integrates Backend APIs. |
| Vo Van Minh | Analyst | Analyzes CEO Memo documents, defines Business Requirements (BRD), and designs data mapping workflows. |

### 2.2 Stakeholders

| Stakeholder | Role | Interest |
| --- | --- | --- |
| Company X | Client | Expects a reliable integrated HR & Payroll system. |
| MSc. Nguyen Dang Quang Huy | Instructor | Provides academic guidance, approves case studies, and evaluates the team’s learning outcomes. |
| Development Team | Project Team | Applies system integration knowledge in practice and completes course requirements. |
| HR & Payroll Managers | End Users | Need a tool to reduce manual data consolidation and inconsistent reporting. |

## 3. Project Scope and Deliverables

### 3.1 Project Objectives

Analyze HR and Payroll data structures: Examine the database schemas of both SQL Server (HUMAN_2025) and MySQL (PAYROLL) to understand data types and relationships.

Design API structure: Architect a RESTful API layer to facilitate secure communication and data exchange between the two systems.

Build the Dashboard system: Develop a centralized, visual interface (Dashboard) for real-time management and monitoring.

Develop reporting and analytics functions: Implement features to generate dynamic reports and analyze key metrics

Ensure data consistency: Establish synchronization mechanisms to guarantee that data remains identical and accurate across both databases.

### 3.2 Project Deliverables

| No. | Deliverable | Description | Due Week |
| --- | --- | --- | --- |
| 1 | Project Proposal | Defines project goals, problems, and proposed solutions. | Week 1 |
| 2 | Project Plan | Develops a detailed plan, schedule, resource allocation, and risk management strategy. | Week 2 |
| 3 | System Design | Designs the overall system architecture. | Week 3 |
| 4 | API Specification | Documentation for API design, detailing the connection between HR and Payroll systems. | Week 4 |
| 5 | Dashboard UI | Designs the Dashboard user interface (UI/UX). | Week 5 |
| 6 | Core Backend & Integration | Source code handling HR and Payroll data synchronization via API. | Week 6 |
| 7 | Security Module, RBAC | Designs security protocols and User Role-Based Access Control. | Week 6 |
| 8 | Testing Report | Testing reports and quality metrics. | Week 8 |
| 9 | Final Product | Finalized source code, documentation, and project summary. | Week 9 |

### 3.3 Work Breakdown Structure (WBS)

| Phase | Main Tasks | Key Deliverables | Duration |
| --- | --- | --- | --- |
| 1 | Analyze CEO Memo and define business issues | Project Proposal | Week 1 |
| 1 | Develop a detailed plan, project schedule, and risk management plan. | Project Plan | Week 2 |
| 2 | Design system architecture, Authentication Database schema, and Data Mapping. | System Design Document | Week 3 |
| 2 | Define API structures for HR and Payroll integration | API Specification | Week 4 |
| 3 | Design and develop frontend interfaces. | Dashboard UI | Week 5 |
| 3 | Implement core backend APIs for data synchronization and payroll logic. | Core Backend & Integration | Week 6 |
| 3 | Develop Authentication module (Login/Logout), RBAC. | Authentication & Security Module | Week 7 |
| 4 | Execute Unit & Integration testing. Test API. Test data integration. | Testing Report | Week 8 |
| 5 | Finalize source code, write project summary report. | Final Product | Week 9 |

## 3.4 Development Process

### 3.4.1 Overview

Waterfall Model:

A project management model where development flows downwards through phases (Analysis → Design → Implementation → Testing → Deployment).

Each phase must be completed before the next begins.

Why use Waterfall Model:

The project scope and constraints are clearly defined in the "CEO MEMO".

It allows for easy tracking of weekly progress and deliverables

### 3.4.2 Lifecycle Phases

| Phase | Description | Deliverables |
| --- | --- | --- |
| 1 | Requirement Analysis (Case Study 1): Identify business problems from the CEO Memo, define project objectives, and specify integration requirements between HUMAN_2025 and PAYROLL systems. | Project Proposal, BRD |
| 2 | System Design (Case Study 2): Design system architecture, database schemas, and data mapping strategies. | Architecture Diagram, ERD. |
| 3 | Backend Integration (Case Study 3): Develop APIs for reading/writing data and implement synchronization logic. | Backend Source Code, API Specifications. |
| 4 | Security Implementation (Case Study 4): Build authentication database, RBAC roles, and audit logging module. | Security Module Code, Auth DB Script. |
| 5 | Frontend & Reporting (Case Study 5): Implement Dashboard UI, visualization charts, and automated alerts. | UI Specification. |

### 3.4.4 Iteration and Review Cycles

Weekly Meeting:

The team meets weekly to track progress, assign tasks, and resolve technical blockers.

Instructor Reviews:

Formal reviews are conducted after each Case Study to validate deliverables before proceeding to the next phase

Version Control (GitHub):

All code changes require a Pull Request before merging.

Testing Cycles:

Unit Testing: Performed continuously by developers during the coding phase.

Integration Testing: Executed at the end of each iteration to ensure data synchronization between HR and Payroll systems functions correctly without errors.

### 3.4.5 Tools and Development Environment

| Category | Tools | Purpose |
| --- | --- | --- |
| Project Management | Trello / GitHub Projects | Task tracking and progress monitoring |
| Documentation | Word | Creating project deliverables (Proposal, SRS, Project Plan). |
| Backend Development | Python | Developing RESTful API services and handling data synchronization logic. |
| Database | MySQL, SQL Server | Storing and managing core data for Payroll (MySQL) and HR (SQL Server). |
| Frontend Development | ReactJs | Building the interactive Dashboard UI and visualizing data charts. |
| Testing | Postman, Jest / PyTest / xUnit | Performing API integration testing (Postman) and Unit testing (Jest/PyTest). |
| Communication | Discord, Messenger | Facilitating internal team communication and weekly meetings. |

## 4. Schedule and Milestones

| Milestone ID | Description | Target Week | Status |
| --- | --- | --- | --- |
| M1 | Project Proposal reviewed and approved | Week 1 | Pending |
| M2 | Project Plan completed and submitted | Week 2 | Pending |
| M3 | SRS and UI/UX Design finalized | Week 4 | Pending |
| M4 | Backend APIs for HR & Payroll integration developed | Week 6 | Pending |
| M5 | Security and RBAC module implemented | Week 8 | Pending |
| M6 | Final Dashboard and Reports integrated | Week 11 | Pending |
| M7 | Project Deployment and Handover | Week 12 | Pending |

## 5. Resource and Tools Plan

### 5.1 Software and Tools

| Tool | Purpose |
| --- | --- |
| Visual Studio / VS Code | Backend development (Python) |
| SQL Server Management Studio | Restore Payroll database |
| MySQL Workbench | Restore HR database |
| React | Frontend development |
| GitHub | Version control |
| Discord | Meeting |

### 5.2 Human Resources

- Communication flow:

Daily meeting: 15 minutes

Official Channel: All major decisions must be confirmed via Email or Trello.

- Work flow:
Data Analyst <-> PM <-> Dev
Backend <-> Frontend
Tester <-> Dev/PM

- Rules:
Hand-over from Analyst to Developers: Must include clear documentation of data logic and business rules.

Hand-over from Backend to Frontend: Must include API Documentation

Hand-over from Development to Tester: Must be accompanied by a "Release Note" listing exactly which new features are ready to be tested

## 6. Risk Management

| Risk ID | Description | Probability | Impact | Mitigation Strategy |
| --- | --- | --- | --- | --- |
| R1 | Database connection errors | Medium | High | Validate connection strings and handle exceptions gracefully. |
| R2 | Requirement changes | High | High | No new features are allowed in the second half of the project. |
| R3 | Poor data quality | Low | High | The data analyst must review the data file in the first week to catch errors early. |
| R4 | API Integration Mismatch | Medium | High | Agree on only one format first. |
| R5 | "Works on My Machine" | Medium | Medium | Deploy Weekly. Upload the code to the real server often to catch these errors early. |

## 7. Quality and Communication Plan

### 7.1 Quality Assurance

To ensure the Integrated HR & Payroll Dashboard operates stably and meets the course requirements, the team applies the following quality control standards and procedures:

Applied Standards:

- Documentation: Adheres to the IEEE 830 -1998 standard structure for Software Requirements Specification (SRS) and design documentation.

- Coding Standards:

- Backend: Follows standard RESTful API practices (correct usage of HTTP methods GET/POST/PUT, plural noun resource naming). Adheres to Clean Code principles (meaningful variable names, comprehensive comments).

- Database: Enforces consistent naming conventions (CamelCase or Snake_case) and ensures data integrity via Foreign Keys.

- Security: Implements JWT for stateless authentication and HTTPS for secure data transmission.

Testing Strategy: The team performs rigorous testing for each deliverable before submission:

- Unit Testing: Developers verify individual processing functions (e.g., salary calculation logic, employee data retrieval) before committing code to GitHub.

- Integration Testing: Verifies the communication between the API layer and the two databases (SQL Server & MySQL). Ensures data fetched from heterogeneous sources is correctly mapped into a single JSON object.

- Data Consistency Check: Executes test scenarios with mismatched data

- Code Review: All new code on GitHub must be reviewed by at least one other team member before merging into the Main branch.

### 7.2 Communication Plan

| Method | Frequency | Purpose | Participants |
| --- | --- | --- | --- |
| Weekly Team Meeting | Weekly | Review past progress, assign new tasks for the week, and resolve technical blockers. | All members |
| Instructor Consultation | Per Phase | Report project progress, seek feedback on documentation, and Demo the product for approval. | All members, Instructor |
| GitHub Updates | Daily | Update source code, track change history, and manage Version Control. | Developers, Tester |
| Instant Messaging (Discord/Messenger) | Daily | Quick discussions, urgent notifications, and deadline reminders. | All Members |
| Shared Drive/Docs | As needed | Collaborative editing of documents (Proposal, SRS, Plan) and archiving meeting minutes. | All Members |

## 8. Change Control Process

To ensure the project remains within the defined scope and timeline, any proposed changes to the Project Plan, Requirements (SRS), or System Architecture must follow the formal 4-step process outlined below:

Detailed Process

| Step | Step Name | Action Description |
| --- | --- | --- |
| Step 1 | Change Request (CR) | Any team member identifying a need for change must submit a formal request via a "New Issue" on GitHub or a CR form. Required info: Change Description and Reason for Change. |
| Step 2 | Review & Analysis | The Project Manager (PM) and Technical Lead analyze the impact: - Scope: Does it add unplanned modules? - Timeline: Will it delay the current weekly deadline? - Resources: Is the team available to handle this? |
| Step 3 | Approval | Decision making based on analysis: - Minor Changes: PM approves internally. - Major Changes: Must consult the Instructor/Mentor for approval. -> Outcome: Approved or Rejected. |
| Step 4 | Update Version | If approved: 1. Developer implements the code changes. 2. Update the SRS Document and Project Plan to reflect reality. 3. Increment the document version number. |

Change Request Log Template

| CR ID | Change Description | Requested By | Impact Analysis | Status | Approval Date |
| --- | --- | --- | --- | --- | --- |
| CR-01 | Add "Forgot Password" feature | Frontend Dev | Low (Takes 1 day) | Approved | 28/01/2026 |
| CR-02 | Switch DB from MySQL to Oracle | Backend Dev | High (Requires API re-write) | Rejected | 29/01/2026 |
| CR-03 | Add PDF Report Export feature | Instructor | Medium (Takes 2 days) | Approved | 30/01/2026 |

## 9. Project Closure

Document and Source Code:

- Source Code: Deliver full code for the Dashboard (Frontend), Integration APIs (Backend), and Authentication Database scripts.

- Documentation: Provide System Architecture diagrams, API Specifications, UI Specification.

Presentation and Demo:

- Demonstrate that the website successfully connects the HR and Payroll systems.

- Show all the features that reqiures and working properly.

Final Report:

- Testing: Results from integration testing confirming data accuracy and security testing results.

- Lessons Learned: How to work with APIs, databases and how to integration systems.

- Future Work: Suggestions for a mobile employee app and add AI features.

## 10. Appendix

Appendix A: Detailed Project Schedule

Detailed Gantt chart will be generated using MS Project and attached in the next version of this document

Appendix B: Project Resources & Repository Links

https://github.com/Siba-2005T/Integrated-HR-Payroll-System

https://trello.com/b/ViLUQiaY/integrated-hr-payroll-system